## Sheet1
Sprint | UI Developer | Python Dev 1 (LLM) | Python Dev 2 / Backend | Java Backend Engineer | Product Owner
Sprint 1 (Aug 28 – Sep 10) – Setup & Foundations and Engage MRM | Focus: UI Bootstrap and SetupTasks: Setup React project (Dont Clone from DART) Create Onboarding UI / SOP and Mapping Create Component place holder for Data layer Implement login + routing Create dashboard placeholder | Focus: LLM Service for SOP: Setup Langgraph - Move LLM Demo API to Pipeline Implement SOP parser stub (dummy extraction) Setup CI/CD for Python- Unit test pipeline Invoice MRM to review the SOP (prompt) | Focus: Data Integration SetupTasks: Connect with ICMP Integration and MRM Team Connect to Database Layer perform AppAssement - Intake Request for Intake | Focus: Backend FoundationTasks: Setup Spring Boot project- SOP Read/Write/Version Batch Process and Invoke Python API stub Async configuration (Kafka) Dashboard API Preperation | Intake Request and complete AppAssesment for MACP and Corefax ICMP Intake and Arch Decision Business Sign off on SOP without any deviation MRM Colloboration Database Intake request for both the usecase
Sprint 2 (Sep 11 – Sep 24) – Onboarding Flow confirmation | Focus: Process Onboarding UITasks: Build Onboarding form (name, SOP upload, exceptions, metadata) File upload widget- Display process onboarding status in dashboard Input validation for fields | SOP Parsing ServiceTasks:- Implement text parsing pipeline- Extract process steps from SOPs Suggest exception handling rules Return JSON results to backend - Handle edge cases in parsing | Focus: Metadata PersistenceTasks: Store onboarding metadata in DB- Create self-discovery stub (auto-detect missing details) API integration with LLM service | Focus: Onboarding APIsTasks:- API for form submissions- API for file storage & retrieval- Persist metadata in DB Connect Python parsing service results to UI | Finalize and lock the SOP Data Integration for lower environment enabled Finalize the ICMP Extraction Pipeline
Sprint 3 (Sep 25 – Oct 8) – Validation Workflow in Dev | Focus: Validation and Dashboard Per QA Project Build UI to review results in Dashboard with Agent Execution e.g) Corefax Agent 1:3 Approve/reject/edit metadata- Add inline comments/notes- Submit final validation | Focus: Complete Reasoning Agent Integration with ICMP Prompt Management API Connect with all SOP via API Connect Data Integration Agent | Focus: Complete Data Integration Agent Integration with all Datalayer using JavaAPI to collect the Data Give GroundTruth Data to MRM team | Focus: Workflow OrchestrationTasks Review the Results with Business Integration with ICMP DocViewer | Dev Signoff
Sprint 4 (Oct 9 – Oct 22) – UAT Ready and Testing and Buffer due to Holiday and Overflow from Sprints | Validate the UI with Business Authentication and Authorization MultiTenant - Concole Values | Test for Scale for Agentic QA Workflow for both the usecase | Test for Scale for Data Integation Workflow for both the usecase | Focus: Metrics AggregationTasks:- Collect execution logs- Performance aggregation (bot runtime, retries, failures)- Optimize metrics DB queries | UAT Validation
Sprint 5 (Oct 23 – Nov 5) – UAT Ready and Testing and Buffer due to Holiday | Focus: Reporting DashboardTasks:- Build process metrics dashboard- Charts: Success %, Failure %, Validation Time- Drilldown reports- Export PDF/Excel | Focus: Reporting ServiceTasks:- Aggregate metrics from onboarding + validation- Metrics: #Processes onboarded, #Exceptions auto-handled, human interventions- Generate API | Focus: Reporting ServiceTasks:- Aggregate metrics from onboarding + validation- Metrics: #Processes onboarded, #Exceptions auto-handled, human interventions- Generate API | Focus: Reporting APIsTasks:- Build reporting APIs- Executive report generation (summary PDFs)- Secure API endpoints | UAT Signoff
Sprint 6 (Nov 6 – Nov 15) – Pre-Prod & Go Live | Focus: Final UI PolishTasks:- Responsive design- Accessibility compliance- Fix UAT issues- Final styling pass | Focus: Moving Code to Prod Improve exception detection accuracy- Optimize inference latency- Fix edge cases from UAT- Final model validation | Focus: Moving Code to Prod Improve exception detection accuracy- Optimize inference latency- Fix edge cases from UAT- Final model validation | Perform the Prod Deployment | Prod Review