## Executive Overview
OBSERVE TO AGENT — 4 Workstream Breakdown for 10X QA Automation
QA Control Discovery Platform ¦ Google ADK ¦ MCP Server ¦ Neo4J ¦ Kafka ¦ MongoDB
| Workstream | Description | Key Technology | Outcome | Complexity | Timeline
WS-1 | Discovery Layer | Observe human QA processes via SKAN, VLM, click streams. Build knowledge graph. Auto-generate SOPs from observed behavior. | SKAN, VLM, iGraphx, Neo4J, HITL | Refined SOPs with full control coverage map | High | Months 1–6
WS-2 | Integration Layer (MCP Registry) | Build universal MCP connectors to all enterprise data sources. Create a single registry of all available data tools for agents. | MCP Server, Google ADK MCP Datatool | Unified data fabric across ICMP, ECM, DB, Email, SharePoint, API, Web, Thick Client | High | Months 1–4
WS-3 | SOP Executor & Validator | Convert refined SOPs into executable ADK agent code. A/B test in UAT, validate in Preprod, promote through staging with engineer sign-off. | Google ADK, MCP Connectivity, Prompt Engineering | UAT-tested, accuracy-validated, engineer-approved agent code ready for production | Very High | Months 3–9
WS-4 | Execution Engine (Run at Scale) | Production runtime that executes validated agents at batch scale. Ingestion via Kafka, agent runtime, MongoDB for results, monitoring dashboard. | Kafka, MongoDB, Agent Runtime, Dashboard | Scalable execution of 2,500+ controls with real-time monitoring and status tracking | High | Months 6–12
KEY METRICS & TARGETS
| Metric | Current State | Target (WS-1+2) | Target (WS-3) | Target (WS-4)
| Control Discovery Rate | Manual — weeks per control | Auto-discover from observation | Auto-generate agent code | Execute at batch scale
| SOP Coverage | ~30% documented | 95%+ via SKAN/VLM observation | 100% validated in UAT+Preprod | 100% monitored in production
| Data Source Connectivity | Siloed, manual access | Unified MCP registry (10+ connectors) | UAT + Prod MCP configs | Full production connectivity
| Accuracy Validation | None (trust human process) | HITL accuracy loop on SOPs | A/B testing Human vs AI | Continuous monitoring + drift detection
| Time to Automate 1 Control | 4–6 weeks | < 1 week (SOP generation) | < 1 week (code + validation) | < 1 day (deploy + run)
| Controls Running at Scale | 0 | N/A (discovery phase) | 120+ validated | 2,500+ in production

## WS-1 Discovery Layer
WORKSTREAM 1: DISCOVERY LAYER
Observe human QA workflows → Build Knowledge Graph → Auto-generate SOPs
# | Component | Detailed Description | Technology | Input | Output | Integration Point | Status
1.1 | SKAN Output Capture | QA Analyst's machine is observed via SKAN tool. Captures screen recordings (.mp4), click streams, and process maps as structured JSON output. This is the raw observation of how humans perform QA controls. | SKAN Tool | Human QA workflow | Click stream .mp4 + Process Map JSON | Feeds into VLM for analysis | Build
1.2 | Vision Language Model (VLM) | Processes SKAN video recordings and screenshots using a Vision Language Model to understand what the QA analyst is doing: which screens they visit, what data they read, what decisions they make, and in what sequence. | VLM (Gemini Vision / GPT-4V) | SKAN .mp4 + screenshots | Structured workflow understanding | Feeds process understanding to SOP Gen | Build
1.3 | Click Stream Analysis | Analyzes the click-by-click interaction data from SKAN to map the exact navigation path: which applications opened, which fields checked, which buttons clicked, time spent per step. | SKAN JSON Parser | SKAN JSON output | Navigation map + timing data | Enriches SOP with step-by-step detail | Build
1.4 | Process Map Generation | Converts SKAN output into formal process maps using iGraphx. These visual process flows show decision points, branching logic, exception paths, and data source touchpoints. | iGraphx | SKAN JSON + VLM output | Formal BPMN process maps | Visual input for SOP refinement | Build
1.5 | Neo4J Knowledge Graph | All discovered controls, their process steps, data sources, decision points, and relationships are stored in a Neo4J knowledge graph. This becomes the 'Control Genome' — the living taxonomy of all QA controls. | Neo4J Enterprise | Process maps + extracted controls | Knowledge Graph for Controls | Central brain for all workstreams | Build
1.6 | SOP Generation (Coverage) | Automatically generates Standard Operating Procedures from the observed process maps and knowledge graph. Calculates SOP coverage: what % of actual human behavior is captured in the generated SOP. | LLM (ADK Agent) + Neo4J | Knowledge Graph + Process Maps | Draft SOPs with coverage score | Feeds into WS-3 for execution | Build
1.7 | Human-in-the-Loop (HITL) | Subject matter experts review auto-generated SOPs for accuracy. If accuracy is not achieved, feedback is looped back to refine the VLM understanding and SOP generation. Iterative until approved. | Pega / Custom Review UI | Draft SOPs | Accuracy decision (Yes/No) | Feedback loop to SKAN + VLM | Build
1.8 | Accuracy Check & Refinement | Decision gate: Has the generated SOP achieved required accuracy vs. actual human process? If No → loop back to HITL for further refinement. If Yes → produces the 'Refined SOP' ready for WS-3. | Scoring Engine | HITL feedback + SOP | Refined SOP (approved) | Handoff to WS-3 SOP Executor | Build
1.9 | Refined SOP Output | The final, approved SOP that accurately captures the human QA process. This is the gold standard input for WS-3 where it will be converted into executable ADK agent code. | Document + JSON Schema | Accuracy-approved SOP | Production-ready SOP document | Primary input to WS-3 | Deliverable
DEPENDENCIES & RISKS
# | Dependency / Risk | Description | Impact | Mitigation
D1 | SKAN Tool Deployment | SKAN must be installed on QA analyst machines to capture workflows | HIGH — blocks all discovery | Prioritize SKAN rollout to pilot group of 10 analysts
D2 | VLM Accuracy | VLM must correctly interpret screen recordings of complex multi-app workflows | HIGH — incorrect understanding = wrong SOPs | Iterative HITL loop; start with simple controls first
D3 | Neo4J Schema Design | Graph schema must accommodate all control types across all domains | MEDIUM — rework if schema is wrong | Co-design schema with architects + domain experts
D4 | QA Analyst Cooperation | Analysts must allow SKAN observation of their daily work | MEDIUM — resistance from teams | Position as augmentation, not surveillance; involve analysts in review

## WS-2 Integration Layer
WORKSTREAM 2: INTEGRATION LAYER (MCP REGISTRY)
Build universal MCP connectors → Register all data tools → Enable agent data access
# | MCP Connector | Detailed Description | Technology | Source System | Data Type | Agent Access Pattern | Priority
2.1 | ICMP Metadata | MCP connector that provides read-only access to ICMP document imaging system. Retrieves document metadata, case references, image pointers, and correspondence records. Critical for document-heavy controls. | MCP Server + JDBC | ICMP (Production) | Document images, metadata, case files | Read-only query by control_id, doc_type | P1 — Critical
2.2 | ECM Document | MCP connector for Enterprise Content Management. Retrieves full document content — contracts, KYC docs, loan packages, regulatory filings. Supports PDF, DOCX, scanned image formats. | MCP Server + ECM API | ECM (Production) | Contracts, KYC docs, agreements, filings | Read-only retrieval by doc_id, doc_type | P1 — Critical
2.3 | Database Connector | Generic database MCP connector supporting JDBC/ODBC connections to any relational database. Used for ERP data, core banking records, transaction tables, reference data. | MCP Datatool + JDBC/ODBC | Oracle, SQL Server, DB2 | Structured records, transaction data | Parameterized SQL query via MCP | P1 — Critical
2.4 | Email Extraction | MCP connector that retrieves and parses email content. Used for controls that validate email-based communications, notifications, or approvals. | MCP Server + Graph API | Exchange / O365 | Email body, attachments, metadata | Query by sender, date range, subject | P2 — Important
2.5 | SharePoint | MCP connector for SharePoint document libraries. Retrieves SOPs, policy documents, and evidence files stored in SharePoint sites. | MCP Server + Graph API | SharePoint Online | SOPs, policies, evidence docs | Read by site, library, folder path | P2 — Important
2.6 | API Gateway | Generic REST/GraphQL API MCP connector. Wraps any HTTP-based service as an MCP tool. Used for vendor portals, regulatory feeds, market data. | MCP Server + HTTP | External APIs | JSON/XML responses | On-demand HTTP call with auth | P2 — Important
2.7 | Web Extraction (Playwright) | Browser automation MCP connector using Playwright. Navigates to web applications, extracts data from screens that don't have APIs. Handles login, navigation, data scraping. | MCP Server + Playwright | Web Applications | Screen-scraped data | Automated browser session | P2 — Important
2.8 | Thick Client Extraction | MCP connector for desktop thick-client applications. Uses UI automation to interact with native Windows/Java applications that have no API or web interface. | MCP Server + RPA/UI Automation | Desktop Applications | Screen capture + OCR data | UI automation + field extraction | P3 — Future
2.9 | MCP Registry | Central registry that catalogs ALL available MCP tools, their schemas, access patterns, and which controls use them. Registered in Neo4J as DataSource nodes. | Neo4J + Registry Service | All above connectors | Tool metadata, schemas, access policies | Agent queries registry to find tools | P1 — Critical
*Note: Mainframe Application extraction is OUT OF SCOPE for initial release

## WS-3 SOP Executor
WORKSTREAM 3: SOP EXECUTOR & VALIDATOR
Refined SOP → Generate ADK Code → UAT Test → Preprod Validate → Engineer Approval → Production Ready
# | Pipeline Stage | Detailed Description | Technology | Input | Output | Decision Gate
3.1 | Refined SOP Intake | Receives the approved Refined SOP from WS-1 Discovery Layer. Also receives MCP Connectivity configuration specifying which MCP tools are available for this control. | SOP Portal + Config Store | Refined SOP (from WS-1) | SOP + MCP Config ready for code gen | —
3.2 | UAT Configuration | Sets up the UAT environment configuration: which MCP tools to use, data subset selection, test transaction IDs, expected outcomes from human baseline. | YAML Config Files + Git | SOP + MCP Config | UAT-ready configuration | —
3.3 | Generate ADK Code | AI agent (powered by LLM) reads the Refined SOP + UAT Config and auto-generates Google ADK agent code. This includes: data extraction steps, validation logic, decision rules, exception handling, and evidence packaging. | Google ADK + LLM (Gemini/Claude) | Refined SOP + Config | Draft ADK Agent Code | —
3.4 | Code Review | Generated ADK code is reviewed by engineering team. Checks for: correctness vs SOP, security compliance, MCP tool usage patterns, error handling, and logging standards. | Code Review Tool / IDE | Draft ADK Code | Review feedback | Changes Needed?
3.5 | Feedback Loop — Prompt + Code Editor | If changes are needed: Engineering provides feedback. The Prompt + Code Editor refines the LLM prompt and regenerates the ADK code. This is an iterative loop until code passes review. | Prompt Engineering + LLM | Review feedback | Revised ADK Code | Loop until approved
3.6 | Execute Agent (UAT) | Approved code is executed in UAT environment. Agent runs against UAT test transactions using UAT MCP configurations. Results compared to expected outcomes. | Google ADK Runtime + UAT MCP | Reviewed ADK Code + UAT Config | UAT execution results | Accuracy Achieved?
3.7 | Accuracy Gate — UAT | Decision: Did the agent achieve required accuracy in UAT? If No → return to Prompt + Code Editor for refinement. If Yes → promote to Preprod with Production MCP connectivity. | Scoring Engine | UAT results vs expected | Go/NoGo for Preprod | Yes → Preprod / No → Iterate
3.8 | Production MCP Connectivity | For Preprod testing: Configure agent to read from Production systems (ICMP, ECM, CoreTax, SOR) in READ-ONLY mode via MCP Server. Same production data the human uses. | MCP Server (Prod Read-Only) | Approved UAT code | Preprod-ready config with Prod access | —
3.9 | Execute Agent (Preprod) | Agent runs in Preprod against real production data (read-only). Processes the same transactions humans completed in the last batch. Results compared to human baseline. | Google ADK + Prod MCP (read-only) | Preprod config + Prod MCP | Preprod execution results | Accuracy Achieved?
3.10 | Accuracy Gate — Preprod | Decision: Did the agent match human results with required accuracy (≥95%)? If No → return to feedback loop with production-data-specific insights. If Yes → promote to staging. | A/B Comparison Engine | AI results vs Human baseline | Validated SOP+ADK Code | Yes → Staging / No → Iterate
3.11 | Promote to Staging | Validated code package (SOP + ADK Code + Config) promoted to staging environment for final engineer validation before production deployment. | CI/CD Pipeline | Validated SOP+ADK Code | Staging deployment | —
3.12 | Engineer Validation | Senior Engineer performs final validation in staging. Reviews: accuracy report, edge case handling, error recovery, performance under load. Signs off for production. | Engineering Review | Staging deployment + accuracy report | Engineer-signed code | Go/NoGo for Prod
3.13 | Self-Service Business Validation* | Business team and POs can validate Preprod responses via a self-service platform. Reviews AI decisions, provides feedback, and issues final Go/NoGo for production. | Pega / Self-Service Portal | Preprod results | Business approval | *Note: Business platform

## WS-4 Execution Engine
WORKSTREAM 4: EXECUTION ENGINE (RUN AT SCALE)
Scheduled/Manual Trigger → Kafka Ingestion → Agent Runtime → MongoDB Results → Dashboard Monitoring
# | Component | Detailed Description | Technology | Input | Output | Scale Characteristics
4.1 | Scheduled Start / User Interface | Production execution can be triggered two ways: (1) Scheduled via cron/scheduler for batch processing, or (2) Manual trigger via User Interface for ad-hoc runs. Both publish control execution requests to the ingestion service. | Scheduler + React UI | Schedule config or manual trigger | Execution request | Handles 100+ scheduled triggers/day
4.2 | Ingestion Service | Receives execution requests and publishes them to Kafka topics. Handles request validation, deduplication, prioritization, and rate limiting. Each control execution becomes a Kafka message. | Microservice + Kafka Producer | Execution requests | Kafka messages (control_id, batch_id, config) | Horizontally scalable; handles burst loads
4.3 | Kafka Event Bus | Apache Kafka serves as the central event bus. Decouples ingestion from execution. Provides guaranteed delivery, ordering, and replay capability. Each control type has its own topic partition. | Apache Kafka | Ingestion messages | Ordered event stream for agent consumers | Millions of messages/day; 7-day retention
4.4 | Agent Runtime | The core execution engine. Kafka consumers pull control execution requests and spin up the appropriate ADK agent. Each agent is containerized, isolated, and monitored. Agents execute the validated SOP+ADK code from WS-3. | Google ADK + Kubernetes/GKE | Kafka messages | Control execution results + evidence | Auto-scaling; 50+ concurrent agent executions
4.5 | Agent Execution Engines | Specialized agent instances per control type. Example: Control 1 = BRES Agent (Business Rules Execution), Control 2 = CDCR Agent (Credit Data Cross-Reference). Each agent has its own SOP config, MCP tool set, and validation rules. | ADK Agent Containers | Control config + MCP tools | Pass/Fail + evidence + confidence score | One agent type per Control Family; reusable
4.6 | MCP Production Connectors | Full production MCP connectivity. Agents read from ICMP, ECM, CoreTax, and all SOR systems via the MCP Registry established in WS-2. All access is read-only and fully audited. | MCP Server (Production) | Agent data requests | Production data for validation | Connection pooling; rate-limited per SOR
4.7 | MongoDB Results Store | All execution results stored in MongoDB as 'QA Review Transaction Data'. Each document contains: control_id, doc_id, execution result, confidence score, evidence links, timestamp, agent version. | MongoDB | Agent execution results | Queryable transaction data | Document store scales to millions of records
4.8 | Doc ID Tracking | Every document processed receives a unique Doc ID that tracks it through the entire execution pipeline: ingestion → agent assignment → execution → result → review. Enables full end-to-end traceability. | UUID Generation + MongoDB Index | Ingested document | Unique Doc ID with full lifecycle | Billions of unique IDs
4.9 | Dashboard Service | Real-time dashboard showing: agent execution status, pass/fail rates, processing throughput, queue depth, error rates, SLA compliance. Connects to MongoDB for historical data and Kafka for real-time. | React + Grafana + WebSocket | MongoDB + Kafka streams | Visual monitoring dashboard | Real-time updates; sub-second latency
4.10 | Dashboard & Monitoring | Comprehensive monitoring layer: agent health, resource utilization, accuracy trends, drift detection, alerting on threshold breaches. Feeds into Control Tower for executive visibility. | OpenTelemetry + Grafana + PagerDuty | Agent telemetry + execution metrics | Alerts, trends, SLA reports | Full observability across all agents
4.11 | Update Status | After each execution completes, status is updated back to the source system (Indigo batch tracker) and the Neo4J knowledge graph. Enables closed-loop tracking from request to completion. | Status API + Neo4J Writer | Execution results | Updated control status in source system | Async status updates; retry on failure

## Cross-Workstream Flow
END-TO-END CROSS-WORKSTREAM DATA FLOW
# | Stage | WS-1 Discovery | WS-2 Integration | WS-3 SOP Executor | WS-4 Execution Engine
1 | Observe | SKAN captures human QA process on analyst machine | — | — | —
2 | Understand | VLM + Click Stream analysis extracts workflow steps | — | — | —
3 | Map | iGraphx creates process maps; Neo4J stores knowledge graph | MCP connectors identified from observed data sources | — | —
4 | Generate SOP | Auto-generate SOPs from knowledge graph + process maps | MCP Registry catalogs all required data tools | — | —
5 | Refine | HITL reviews; accuracy loop until Refined SOP approved | MCP tools tested for connectivity + schema validation | — | —
6 | Generate Code | — | MCP tools available in registry | LLM generates ADK code from Refined SOP + MCP config | —
7 | UAT Test | — | UAT MCP config provided | Agent tested in UAT; accuracy measured vs expected | —
8 | Preprod Test | — | Production MCP (read-only) provided | Agent tested against real prod data; A/B vs human baseline | —
9 | Approve | — | — | Engineer + Business approve validated code | —
10 | Deploy | — | Production MCP fully connected | Validated SOP+ADK deployed to production runtime | Agent registered in Execution Engine
11 | Execute | — | MCP serves production data | — | Kafka ingests; Agent Runtime executes at batch scale
12 | Monitor | Knowledge graph updated with execution results | MCP audit logs tracked | Feedback loop if accuracy degrades | Dashboard + Control Tower real-time monitoring

## Timeline & Milestones
12-MONTH IMPLEMENTATION TIMELINE
Workstream / Milestone | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Key Deliverable
WS-1: SKAN Deployment | [12 empty] | SKAN on pilot machines | bar: M1 to M2
WS-1: VLM + Process Mapping | [12 empty] | Process maps for 50 controls | bar: M2 to M4
WS-1: Knowledge Graph Build | [12 empty] | Neo4J Control Genome v1 | bar: M3 to M5
WS-1: SOP Auto-Generation | [12 empty] | Refined SOPs for 200 controls | bar: M4 to M6
WS-2: Core MCP Connectors | [12 empty] | ICMP + ECM + DB connectors live | bar: M1 to M3
WS-2: Extended Connectors | [12 empty] | Email + SharePoint + API + Web | bar: M3 to M5
WS-2: MCP Registry | [12 empty] | Full registry in Neo4J | bar: M4 to M5
WS-3: Code Gen Pipeline | [12 empty] | ADK code gen from SOP working | bar: M3 to M5
WS-3: UAT Framework | [12 empty] | UAT accuracy testing operational | bar: M5 to M6
WS-3: Preprod A/B Testing | [12 empty] | A/B testing with prod data | bar: M6 to M8
WS-3: Engineer Approval Flow | [12 empty] | 120+ controls validated | bar: M7 to M9
WS-4: Kafka + Ingestion | [12 empty] | Kafka pipeline operational | bar: M5 to M7
WS-4: Agent Runtime | [12 empty] | Containerized agent execution | bar: M6 to M8
WS-4: MongoDB + Dashboard | [12 empty] | Results store + monitoring live | bar: M7 to M9
WS-4: Scale to 500+ Controls | [12 empty] | 500+ controls in production | bar: M9 to M11
WS-4: Scale to 2,500+ Controls | [12 empty] | Full portfolio automated | bar: M11 to M12