## Sheet1
Epic | Feature / Story | Description | Est. SP (Story Points)
ONB-01 Tenant Registration | Tenant creation form | Capture tenant name, BU, admin, metadata | 5
| Tenant settings panel | Default templates, DS pools, scenario defaults | 8
ONB-02 Use-Case Creation | Use-case onboarding form | Name, description, objective, rules, outputs | 13
| Field-level validations | Required fields, rule syntax checks | 8
ONB-03 Template Library | Template repository | Common assurance templates | 13
| Wizard setup flow | Step-by-step onboarding wizard | 8
ONB-04 Data-Source Config | DS picker | Select UAT / Non-Prod / Synthetic | 8
| DS validation API | Test connectivity, permission checks | 13
ONB-05 Scenario Definition | Synthetic scenario builder | Thresholds, volumes, date shifts | 8
| Scenario library | Reusable synthetic scenario templates | 5
ONB-06 Workflow + Reviews | Review/approval UI | Reviewer assignment, comments | 13
| Workflow states | Draft → Under Review → Approved | 8
ONB-07 Spec Export | JSON/YAML spec generator | Tenant + use-case + DS + rules | 8
| Runbook preview | Show generated NL runbook | 5
ONB-08 Dashboard & Versioning | Tenant use-case dashboard | List use-cases/status/version | 8
| Version history | Track all spec changes | 8
ONB-09 Notifications | Email/in-app alerts | Submit, review, approve, reject | 5
ONB-10 Audit Logging | Audit events | Who changed what & when | 8

## Sheet2
Epic | Feature / Story | Description | SP
STU-01 Runbook Engine | NL runbook parser | Convert English runbook → agent steps | 13
| Runbook editor | Edit runbook in Canvas UI | 8
STU-02 Action Gallery | Integrate pre-built actions | Fetch data, validate, generate reasoning | 13
| Custom Action SDK | Allow new DS connectors, validations | 8
STU-03 DS Connector Cockpit | DS config UI | Tenant-specific DS connectors | 13
| Connector tester | Validate queries, schema, permissions | 8
STU-04 Synthetic Data Integration | Synthetic generator action | Plug synthetic data into agent tests | 8
| Scenario execution results | Compare outputs vs expectations | 13
STU-05 Reasoning & Explainability | Reason trace viewer | Step-by-step reasoning for SME/audit | 13
| Error replay engine | Replay failed tasks with trace | 8
STU-06 Export Engine | YAML agent config export | Datasource, actions, flows, tests | 8
| Agent.py bootstrap | Python file for orchestrated agent | 13
| Prompt template export | Generate LLM prompt instructions | 5
STU-07 GitHub Integration | Auto-branch creation | Push YAML + Agent.py + Prompt | 8
| Webhook integration | Trigger CI/CD pipeline | 5
STU-08 Agent Versioning | Agent version metadata | v1, v2, rollback, change notes | 8
| Agent artifact diff | Compare agent versions | 5
STU-09 Governance & RBAC | Role mapping | Creator, Reviewer, Engineer | 5
| Approval gate | Push only after review | 8

## Sheet3
Epic | Feature / Story | Description | SP
INT-01 Pipeline Integration | Onboarding → Studio import | Auto-generate runbook + import spec | 13
| Studio → GitHub pipeline | Trigger repo push on export | 8
INT-02 CI/CD | Stage build | Run lint, unit test, safety checks | 8
| Deploy to OCP | Deploy agent APIs per tenant | 13
INT-03 Agent Runtime | API gateway per tenant | Expose agent as API | 13
| Token/auth control | OAuth2/Key-based access | 8
INT-04 Multitenancy | Tenant isolation | Separate DS configs, agent namespaces | 13
| Resource quotas | CPU/memory/usage limits per tenant | 8
INT-05 Monitoring & Ops | Reason trace logs | Store and visualize trace | 8
| Metrics dashboard | Tenant usage, errors, latency | 13
INT-06 Security & Compliance | Logging framework | Audit logs (reasoning + actions) | 8
| Data access controls | DS access per tenant | 13
INT-07 UAT/Prod Controls | Promotion workflow | Move agent from staging → prod | 8
| Gate approvals | SME/manager sign-off | 5