## Executive Overview
QA CONTROL AUTOMATION — TESTING STRATEGY
Three-Lane Validation Framework: Reactive Binary → Preprod Pipeline → Production-Grade Lower Environment
Lane | Strategy Name | Approach | Environment | Data Source | Validation Type | Key Benefit | Key Limitation
Lane 1 | Reactive Binary Validation | Compare manual human QA results against AI-processed results post-execution | Production (Post-Hoc) | Completed manual QA reviews + AI reviews of same items | Binary (Pass/Fail, Yes/No) | Quick confidence: proves AI matches human outcomes | No reasoning comparison; purely reactive; limited to binary outcomes
Lane 2 | Preprod Pipeline Replay | Replay completed production batch jobs in a Prod-mirrored Preprod environment using AI agents only | Preprod (Prod-Fix) | Production batch data replayed in isolated Preprod | Full pipeline validation (end-to-end) | Tests complete AI pipeline with real prod data; no human access needed | Requires Preprod env setup; time & infrastructure investment
Lane 3 | PDiLL — Prod Data in Lower Env | Bring ECM production document types to lower environments for prompt & pipeline testing | Lower Environment (UAT/SIT) | Production document types from ECM replicated to lower env | Prompt + Pipeline + Document Quality | Bridges Lane 1 & Lane 2 gaps; validates prompts against real doc quality | Requires ECM team coordination; document freshness management
COMPARATIVE ANALYSIS
Dimension | Lane 1: Reactive Binary | Lane 2: Preprod Replay | Lane 3: PDiLL
Setup Complexity | Low — uses existing prod data | High — full Preprod env required | Medium — ECM coordination needed
Time to First Result | Days | Weeks to Months | 1–2 Weeks (after ECM setup)
Validation Depth | Shallow — binary only | Deep — full pipeline | Medium-Deep — prompt + doc quality
Reasoning Visibility | None — no AI reasoning captured | Full — complete agent trace logs | Full — prompt-level debugging
Data Authenticity | Real prod data (post-hoc) | Real prod data (replayed) | Real prod documents (replicated)
Human Involvement | High — requires completed human reviews | None — system-only access | Low — only for ECM coordination
Scalability | Limited by human review throughput | High — batch replay at scale | Medium — depends on ECM pipeline
Risk Level | Zero — read-only comparison | Low — isolated Preprod | Low — isolated lower env
Production Readiness Signal | Moderate — confirms outcome parity | Strong — proves pipeline works | Strong — validates prompt quality
Recommended Phase | Phase 1 (Immediate) | Phase 2 (Foundation) | Phase 3 (Optimization)

## Lane 1 — Reactive Binary
LANE 1: REACTIVE BINARY VALIDATION
Compare manually processed QA reviews against AI-processed reviews on the same items. Validates Pass/Fail parity.
✓ PROS: Quick confidence on AI vs Human outcomes ¦ Uses existing production data ¦ Zero infrastructure setup ¦ Immediate start |  |  |  |  | ✗ CONS: Reactive only ¦ No reasoning comparison ¦ Binary validation (Pass/Fail) ¦ Human review bottleneck
# | Phase | Task Name | Description | Owner | Input | Output / Deliverable | Acceptance Criteria | Dependencies | Duration
1.1 | Data Collection | Extract Completed Human QA Reviews | Pull dump of all manually completed QA process reviews from production system (Pega/ICMP). Include control ID, review date, reviewer, outcome (Pass/Fail), document references. | QA Operations Lead | Production QA system access | Human_QA_Dump.csv with columns: ControlID, ReviewDate, Reviewer, Outcome, DocRefs, ControlFamily | Min 500 completed reviews across 10+ control families; data from last 90 days | Prod system access approval | 3 days
1.2 | Data Collection | Extract AI-Processed Reviews | Run the same QA control items through the AI agent pipeline (ADK agents). Capture AI decision, confidence score, reasoning summary, processing time. | AI Engineering Lead | Same control items from Task 1.1 | AI_QA_Results.csv with columns: ControlID, AIOutcome, ConfidenceScore, ProcessingTime, AgentID | All items from 1.1 processed; no failures > 2% | Task 1.1 complete; AI pipeline deployed | 5 days
1.3 | Data Preparation | Normalize & Align Datasets | Join human and AI datasets on ControlID. Normalize outcome fields (Pass/Fail standardization). Flag mismatches. Create unified comparison dataset. | Data Engineer | Human_QA_Dump.csv + AI_QA_Results.csv | Unified_Comparison.csv with match/mismatch flags per record | 100% join rate; zero orphan records; standardized outcome encoding | Tasks 1.1 + 1.2 complete | 2 days
1.4 | Binary Validation | Compute Match Rate — Overall | Calculate overall agreement rate: (Matching Outcomes / Total Reviews) × 100. Target ≥ 95% match rate for Go decision. | QA Analyst | Unified_Comparison.csv | Overall Match Rate (%) — single KPI | Match rate computed accurately; confidence interval reported | Task 1.3 complete | 1 day
1.5 | Binary Validation | Compute Match Rate — By Control Family | Break down match rate by each Control Family (KYC, AML, Credit, Tax, etc.). Identify families with < 90% match for investigation. | QA Analyst | Unified_Comparison.csv | Match_Rate_By_Family.xlsx — pivot table with family-level metrics | All families analyzed; low-performing families flagged | Task 1.3 complete | 1 day
1.6 | Binary Validation | Compute Match Rate — By Outcome Type | Separate analysis for Pass→Pass, Fail→Fail, Pass→Fail (false negative), Fail→Pass (false positive). Quantify each quadrant. | QA Analyst | Unified_Comparison.csv | Confusion_Matrix.xlsx — 2×2 matrix with counts and percentages | All 4 quadrants populated; false positive/negative rates calculated | Task 1.3 complete | 1 day
1.7 | Mismatch Analysis | Deep-Dive Mismatch Investigation | For every mismatched item, pull source documents, review human notes, and AI reasoning. Categorize root cause: data issue, prompt gap, edge case, human error. | Senior QA Engineer | Mismatch records + source documents | Mismatch_Root_Cause.xlsx — each mismatch with categorized root cause | 100% mismatches investigated; root causes categorized into ≤ 6 buckets | Tasks 1.4–1.6 complete | 5 days
1.8 | Mismatch Analysis | Identify Human Error Cases | Separate mismatches where the HUMAN was wrong and AI was correct. This strengthens the AI confidence narrative. | Senior QA Engineer + Domain SME | Mismatch_Root_Cause.xlsx | Human_Error_Cases.xlsx — validated cases where AI outperformed human | Each case validated by SME; documented with evidence | Task 1.7 complete | 3 days
1.9 | Reporting | Build Validation Dashboard | Create executive dashboard: overall match %, family breakdown, confusion matrix, trend over time, mismatch categories pie chart. | Data Visualization Lead | All validation outputs | Lane1_Validation_Dashboard (PowerBI / Tableau) | Dashboard reviewed by stakeholders; all metrics accurate | Tasks 1.4–1.8 complete | 3 days
1.10 | Reporting | Generate Executive Summary Report | One-pager: match rate KPI, top mismatches, human error findings, recommendation (Go / Conditional Go / No-Go for Lane 2). | QA Strategy Lead | Dashboard + all analysis | Lane1_Executive_Report.docx — Go/No-Go recommendation | Reviewed by VP QA; recommendation documented | Task 1.9 complete | 2 days
1.11 | Feedback Loop | Feed Mismatches Back to AI Pipeline | Update AI prompts, rules, and agent configs based on mismatch root causes. Retrain/fine-tune where needed. | AI Engineering Lead | Mismatch_Root_Cause.xlsx | Updated agent configs; patch notes documenting changes | All addressable mismatches resolved; re-run shows improvement | Task 1.7 complete | 5 days
1.12 | Re-Validation | Re-Run Binary Validation Post-Fix | Repeat Tasks 1.2–1.6 after AI pipeline updates. Measure improvement in match rate. Target ≥ 97%. | QA Analyst + AI Eng | Updated AI pipeline + same human dataset | Updated match rates; improvement delta documented | Match rate improved; remaining gaps documented | Task 1.11 complete | 5 days

## Lane 2 — Preprod Replay
LANE 2: PREPROD PIPELINE REPLAY (PROD-FIX ENVIRONMENT)
Replay completed production batch jobs in an isolated Preprod environment. System-only access — no human involvement. Validates complete AI pipeline end-to-end.
✓ PROS: Full pipeline confidence ¦ Uses real prod data ¦ Prod-mirror fidelity ¦ No human bottleneck ¦ Batch-scale testing |  |  |  |  | ✗ CONS: Preprod setup time & cost ¦ Infrastructure mirroring complexity ¦ Batch replay orchestration needed
# | Phase | Task Name | Description | Owner | Input | Output / Deliverable | Acceptance Criteria | Dependencies | Duration
2.1 | Environment Setup | Provision Preprod Infrastructure | Stand up Preprod environment mirroring Production: same servers, DB schemas, network topology, firewall rules. No human user accounts — system service accounts only. | Infrastructure Lead | Prod architecture blueprint | Preprod environment provisioned; architecture validation doc | Mirror verified against Prod checklist (CPU, mem, storage, network) | Infra team allocation; budget approval | 2 weeks
2.2 | Environment Setup | Configure Access Controls | Lock down environment: system-only service accounts, no human SSH/UI access, audit logging enabled. Same IAM roles as Prod for service accounts. | Security Engineer | Prod IAM/RBAC config | Preprod access control matrix; audit log configuration | Zero human access paths; all system accounts documented | Task 2.1 complete | 3 days
2.3 | Environment Setup | Mirror Data Pipeline Configuration | Replicate Kafka topics, MongoDB collections, batch scheduler configs, MCP connector settings from Prod to Preprod. Use same YAML configs with environment-specific endpoints. | Platform Engineer | Prod pipeline configs (YAML) | Preprod pipeline configs; config diff report vs Prod | All pipelines functional; config diff shows only endpoint changes | Task 2.1 complete | 5 days
2.4 | Environment Setup | Deploy AI Agent Stack | Deploy ADK agents, BRES/CDCR agent containers, MCP registry, Neo4J graph — identical versions to Prod. Validate agent health checks. | AI Engineering Lead | Prod container images + deployment manifests | Deployed agent stack; health check report | All agents healthy; version match 100% with Prod | Tasks 2.1–2.3 complete | 3 days
2.5 | Data Replay Setup | Identify Target Batch Jobs | Select completed production batch jobs for replay. Criteria: diverse control families, recent (last 30 days), include edge cases, mix of Pass/Fail outcomes. | QA Strategy Lead | Prod batch execution logs | Batch_Replay_Manifest.xlsx — list of batch IDs, dates, control counts | Min 50 batch jobs selected; ≥ 15 control families represented | Prod log access | 2 days
2.6 | Data Replay Setup | Extract & Stage Batch Data | Extract input data for selected batch jobs from Production. Stage in Preprod MongoDB/Kafka without triggering pipeline execution. Include all referenced documents (ICMP/ECM). | Data Engineer | Batch_Replay_Manifest.xlsx | Staged data in Preprod; data integrity checksum report | Checksums match Prod source; all referenced docs available | Tasks 2.4 + 2.5 complete | 5 days
2.7 | Pipeline Execution | Execute Batch Replay — Wave 1 (10 batches) | Trigger first wave of 10 batch jobs through complete AI pipeline. Monitor execution: agent logs, Kafka throughput, processing times, error rates. | AI Engineering Lead | Staged batch data (Wave 1) | Wave1_Execution_Log.json — per-batch results with timing + outcomes | All 10 batches complete; error rate < 5%; no system crashes | Task 2.6 complete | 3 days
2.8 | Pipeline Execution | Validate Wave 1 Results vs Production | Compare AI pipeline results from Preprod replay against actual Production outcomes. Calculate match rate. Investigate any divergence (data, timing, config). | QA Analyst | Wave1 results + Prod outcomes | Wave1_Validation_Report.xlsx — match rate, divergence analysis | Match rate ≥ 95%; all divergences root-caused | Task 2.7 complete | 3 days
2.9 | Pipeline Execution | Execute Batch Replay — Wave 2 (20 batches) | Scale up: replay 20 additional batch jobs. Focus on control families that showed divergence in Wave 1. Stress-test concurrent execution. | AI Engineering Lead | Staged batch data (Wave 2) | Wave2_Execution_Log.json — 20-batch results | All batches complete; concurrent execution stable; error rate < 3% | Task 2.8 analysis complete | 5 days
2.10 | Pipeline Execution | Execute Batch Replay — Wave 3 (Full Scale) | Replay remaining batch jobs (20+ batches). Full-scale test of pipeline throughput, memory, disk, and agent coordination. | AI Eng + Platform Eng | Staged batch data (Wave 3) | Wave3_Execution_Log.json — full-scale results | Pipeline handles full load; no degradation > 10% | Task 2.9 complete | 5 days
2.11 | Performance Analysis | Benchmark Processing Performance | Compare Preprod AI processing times against Prod human processing times. Calculate throughput gain (target: 10X). Identify bottlenecks. | Performance Engineer | All Wave execution logs + Prod timing data | Performance_Benchmark.xlsx — throughput, latency, resource utilization | 10X throughput target validated; bottlenecks documented | Tasks 2.7–2.10 complete | 3 days
2.12 | Performance Analysis | End-to-End Pipeline Traceability | For 50 sample items, trace complete journey: Kafka ingestion → MCP data fetch → Agent processing → Result storage → Dashboard update. Validate no data loss. | Platform Engineer | Agent trace logs; Kafka offsets; MongoDB writes | Traceability_Report.xlsx — 50 items with full trace | 100% traceability; zero data loss; all steps logged | Tasks 2.7–2.10 complete | 3 days
2.13 | Reporting | Build Preprod Validation Dashboard | Dashboard showing: batch replay results, match rates by wave, performance benchmarks, pipeline health metrics, divergence trends. | Data Visualization Lead | All Wave reports + performance data | Lane2_Preprod_Dashboard (PowerBI / Tableau) | Dashboard reviewed; all metrics validated against source | Tasks 2.8–2.12 complete | 3 days
2.14 | Reporting | Generate Preprod Readiness Report | Executive report: pipeline fidelity score, performance gains, remaining risks, Go/No-Go recommendation for Production deployment. | QA Strategy Lead | Dashboard + all analysis | Lane2_Readiness_Report.docx — Prod deployment recommendation | Reviewed by VP QA + CTO; risk register documented | Task 2.13 complete | 2 days
2.15 | Continuous | Establish Preprod Regression Suite | Convert successful batch replays into automated regression suite. Schedule weekly re-runs to catch drift between Prod and AI pipeline. | QA Automation Lead | Selected batch replays | Automated regression pipeline; weekly execution schedule | Regression runs weekly; alerts on > 2% match rate drift | Task 2.14 complete | 5 days

## Lane 3 — PDiLL
LANE 3: PDiLL — PRODUCTION DATA IN LOWER LEVEL ENVIRONMENT
Bring ECM production document types to lower environments (UAT/SIT) for prompt validation and pipeline testing against real document quality.
✓ PROS: Validates prompts with real doc quality ¦ Bridges Lane 1 & 2 gaps ¦ Lower env flexibility ¦ Prompt iteration speed |  |  |  |  | ✗ CONS: ECM team coordination required ¦ Data masking/PII handling ¦ Document freshness management
# | Phase | Task Name | Description | Owner | Input | Output / Deliverable | Acceptance Criteria | Dependencies | Duration
3.1 | Planning | Inventory Required Document Types | Catalog all document types needed for QA control processing. Map each control family to its required ECM document types (ICMP IDs, ECM categories, metadata). | QA Strategy Lead + Domain SMEs | Control-to-Document mapping from Prod | Document_Type_Inventory.xlsx — full catalog with ECM IDs and control family mapping | All active control families mapped; ≥ 95% document types identified | Control family catalog | 3 days
3.2 | Planning | Engage ECM Team — Kickoff | Formal request to ECM team for PDiLL initiative. Present scope: document types, volumes, frequency of refresh, data masking requirements, target lower environment. | QA Strategy Lead | Document_Type_Inventory.xlsx | ECM_PDiLL_Request.docx — formal request with scope and timeline | ECM team acknowledges request; POC assigned | Task 3.1 complete | 2 days
3.3 | Planning | Define Data Masking & PII Strategy | Work with Data Privacy team to define PII masking rules for production documents moved to lower env. Define what must be masked (SSN, account #) vs what can remain (doc structure, formatting). | Data Privacy Officer + QA Lead | PII classification policy | PDiLL_Data_Masking_Spec.docx — field-level masking rules per doc type | Legal/Compliance sign-off on masking approach | Task 3.2 complete | 5 days
3.4 | ECM Pipeline | Build ECM-to-Lower-Env Extraction Pipeline | ECM team builds automated extraction pipeline: select documents by type → apply PII masking → package for lower env → push to target ECM instance in UAT/SIT. | ECM Engineering Team | PDiLL_Data_Masking_Spec.docx + Document_Type_Inventory.xlsx | Automated ECM extraction pipeline; pipeline architecture doc | Pipeline extracts, masks, and delivers docs end-to-end; tested with 100 samples | Tasks 3.1–3.3 complete | 2 weeks
3.5 | ECM Pipeline | Initial Document Load — Priority Types | Execute first extraction: top 20 document types covering 80% of control families. Validate documents in lower env: readable, correctly masked, metadata intact. | ECM Eng + QA Analyst | Extraction pipeline | Initial_Load_Report.xlsx — 20 doc types, counts, validation status | All 20 types loaded; spot-check 50 docs manually; metadata match ≥ 99% | Task 3.4 complete | 3 days
3.6 | ECM Pipeline | Full Document Load — All Types | Execute complete extraction for all remaining document types. Scale validation across full catalog. | ECM Engineering Team | Document_Type_Inventory.xlsx | Full_Load_Report.xlsx — all doc types loaded with counts and checksums | All required doc types present; zero missing types from inventory | Task 3.5 validated | 5 days
3.7 | ECM Pipeline | Establish Refresh Schedule | Define cadence for document refresh (weekly/monthly). Ensure lower env stays current with Prod document quality/versions. Build automated refresh job. | ECM Eng + Platform Eng | ECM extraction pipeline | Refresh_Schedule.yml — automated cron/scheduler config | Refresh runs on schedule; delta-only updates (not full reload) | Task 3.6 complete | 3 days
3.8 | Prompt Validation | Deploy AI Agent Stack in Lower Env | Deploy ADK agents, MCP connectors, Neo4J graph to lower environment. Configure MCP Datatool to read from lower-env ECM instance. | AI Engineering Lead | Prod agent configs (YAML) adapted for lower env | Deployed agent stack in UAT/SIT; MCP connectivity validated | All agents healthy; MCP reads from lower-env ECM confirmed | Task 3.6 complete | 3 days
3.9 | Prompt Validation | Run Prompt Validation — Wave 1 | Execute AI agents against lower-env documents (Wave 1: 5 control families). Focus on prompt effectiveness: does the prompt extract correct fields from real doc quality? | AI Engineering Lead | Lower-env documents + deployed agents | Wave1_Prompt_Results.xlsx — per-control prompt accuracy metrics | Prompt accuracy ≥ 90% across 5 families; failure modes documented | Tasks 3.5 + 3.8 complete | 5 days
3.10 | Prompt Validation | Prompt Iteration & Tuning | Based on Wave 1 results, refine prompts for each control family. Address formatting differences between Prod and lower-env documents. Re-test after each change. | AI Engineering Lead + Domain SMEs | Wave1_Prompt_Results.xlsx + failure analysis | Updated prompt configs; iteration changelog | Prompt accuracy improved to ≥ 95%; iteration count documented | Task 3.9 complete | 5 days
3.11 | Prompt Validation | Run Prompt Validation — Wave 2 (Full) | Execute across all control families with tuned prompts. Full-scale validation of prompt + pipeline quality against production-grade documents. | AI Engineering Lead | All lower-env documents + tuned prompts | Wave2_Full_Validation.xlsx — all families, all doc types | Overall accuracy ≥ 95%; per-family accuracy ≥ 92% | Task 3.10 complete | 5 days
3.12 | Gap Analysis | Compare Results: Lane 1 vs Lane 3 | Compare binary outcomes from Lane 1 against full prompt validation from Lane 3. Identify cases where Lane 1 showed Pass but Lane 3 reveals prompt weakness. | QA Analyst | Lane1 results + Lane3 results | Cross_Lane_Gap_Analysis.xlsx — gaps between binary and prompt-level validation | All discrepancies documented; root causes mapped | Lane 1 + Task 3.11 complete | 3 days
3.13 | Gap Analysis | Compare Results: Lane 2 vs Lane 3 | Compare Preprod pipeline results (Lane 2) against lower-env prompt quality (Lane 3). Identify pipeline-level vs prompt-level issues. | QA Analyst | Lane2 results + Lane3 results | Cross_Lane2_Lane3_Analysis.xlsx — pipeline vs prompt gap matrix | All gaps categorized: pipeline issue vs prompt issue vs data issue | Lane 2 + Task 3.11 complete | 3 days
3.14 | Reporting | Build PDiLL Validation Dashboard | Dashboard showing: document coverage, prompt accuracy by family, iteration improvement curves, cross-lane comparison matrix, ECM refresh status. | Data Visualization Lead | All Lane 3 outputs | Lane3_PDiLL_Dashboard (PowerBI / Tableau) | Dashboard reviewed; cross-lane metrics validated | Tasks 3.11–3.13 complete | 3 days
3.15 | Reporting | Generate Unified Testing Strategy Report | Final executive report combining all 3 lanes: binary confidence (L1) + pipeline fidelity (L2) + prompt quality (L3). Unified Go/No-Go for Production. | QA Strategy Lead | All 3 lane dashboards + reports | Unified_Testing_Strategy_Report.docx — combined Go/No-Go | Reviewed by VP QA + CTO + Compliance; all 3 lanes pass criteria | All lane reports complete | 3 days

## Cross-Lane Flow
CROSS-LANE TESTING FLOW — HOW THE 3 LANES CONNECT
Stage | Lane | Activity | Gate Criteria | Feeds Into | Timeline | Milestone
1 | Lane 1 | Extract human QA dump from Production | Min 500 reviews available | Stage 2 | Week 1 | Data Extraction Complete
2 | Lane 1 | Run AI pipeline on same items | AI pipeline deployed and healthy | Stage 3 | Week 1–2 | AI Processing Complete
3 | Lane 1 | Binary comparison — compute match rate | Match rate ≥ 95% to proceed | Stage 4 + Stage 7 | Week 2–3 | Binary Confidence Established
4 | Lane 1 | Mismatch root-cause analysis + feedback loop | All mismatches investigated | AI Pipeline Updates | Week 3–4 | Feedback Cycle Complete
5 | Lane 2 | Provision Preprod environment (parallel start) | Infra budget approved | Stage 6 | Week 1–3 | Preprod Environment Ready
6 | Lane 2 | Deploy AI stack + stage batch data | All agents healthy; data staged | Stage 7 | Week 3–4 | Pipeline Deployed
7 | Lane 2 | Batch replay — Waves 1→2→3 | Wave 1 ≥ 95% match; Wave 3 stable | Stage 8 + Stage 12 | Week 4–7 | Pipeline Fidelity Proven
8 | Lane 2 | Performance benchmarking + traceability | 10X throughput validated | Stage 13 | Week 7–8 | Performance Baseline Set
9 | Lane 3 | ECM team engagement + document inventory | ECM POC assigned | Stage 10 | Week 2–3 | ECM Partnership Established
10 | Lane 3 | Build extraction pipeline + initial doc load | Pipeline tested; 20 types loaded | Stage 11 | Week 4–6 | PDiLL Pipeline Live
11 | Lane 3 | Prompt validation Waves 1→2 + tuning | Accuracy ≥ 95% after tuning | Stage 12 | Week 6–9 | Prompt Quality Validated
12 | Cross-Lane | Cross-lane gap analysis (L1 vs L3, L2 vs L3) | All gaps categorized and addressed | Stage 13 | Week 9–10 | Unified Gap Assessment
13 | Cross-Lane | Unified dashboard + executive Go/No-Go report | All 3 lanes pass criteria; CTO sign-off | Production Deployment | Week 10–11 | PRODUCTION GO/NO-GO

## Timeline
QA TESTING STRATEGY — 12-WEEK EXECUTION TIMELINE
Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | Owner
L1: Human QA Data Extraction | ● | [11 empty] | QA Ops Lead
L1: AI Pipeline Processing | ● | ● | [10 empty] | AI Eng Lead
L1: Binary Validation & Analysis |  | ● | ● | [9 empty] | QA Analyst
L1: Mismatch Investigation |  |  | ● | ● | [8 empty] | Sr QA Engineer
L1: Dashboard & Executive Report |  |  |  | ● | ● | [7 empty] | QA Strategy Lead
L2: Preprod Environment Provisioning | ● | ● | ● | [9 empty] | Infra Lead
L2: Deploy AI Stack & Stage Data |  |  | ● | ● | [8 empty] | AI Eng + Platform
L2: Batch Replay Waves 1–3 |  |  |  | ● | ● | ● | ● | [5 empty] | AI Eng Lead
L2: Performance & Traceability | [6 empty] | ● | ● |  |  |  |  | Perf Engineer
L2: Preprod Dashboard & Report | [7 empty] | ● | ● |  |  |  | QA Strategy Lead
L3: ECM Engagement & Doc Inventory |  | ● | ● | [9 empty] | QA Lead + ECM
L3: Build Extraction Pipeline |  |  |  | ● | ● | ● | [6 empty] | ECM Eng Team
L3: Prompt Validation & Tuning | [5 empty] | ● | ● | ● | ● |  |  |  | AI Eng Lead
L3: Cross-Lane Gap Analysis | [8 empty] | ● | ● |  |  | QA Analyst
UNIFIED: Executive Go/No-Go Report | [9 empty] | ● | ● |  | QA Strategy Lead
MILESTONE: Production Deployment Gate | [11 empty] | ● | VP QA + CTO