## Project Timeline
|  |  |  | Q3 | [5 empty] | Q4
| PROJECT WEEK: | Platform - TSP04 / Corefax / EDIP | Primary Owner / Secondary Owner | JUL |  |  |  | AUG | SEP | OCT | NOV |  | DEC
|  |  |  | 1 | 2 | 3 | 4
| Landing Page UI |  | Sankara / Nandini / Sai
Classification UI
Extraction UI
1 | Laison UI | [10 empty] | MVP 1 in Production
Highlighting
2 | Define Data Model |  | Balaram /
Classification API
Extraction Raw API
Count of documents processed
Java backend API
3 | Review Python APIs |  | AJ / Jindal
Extraction logic
Review logic
Validate logic
Layout selection and update
Template review
4 | Move code to GitHub |  | Deepak / Abhijit
Review all libraries
Onboard unapproved libraries
Create AD accounts for Platform, TSP04, Corefax
Strategize move to OCP
Move to Dev infrastructure
Sunrise Process review
5 | ECM MCP Server Integration |  | AJ & Sankara / Anjali
ECM AI Service Integration
Translation Integration
6 | Corefax Review |  | Tanal / Roshan
Corefax Integration Review

## Team Members
1 | Sankara | PE
2 | Deepak | LSE
3 | Balaram | LSE
4 | Abhijit | LSE
5 | AJ | SM
6 | Tanal | Assosiate
7 | Roshan | Assosiate
8 | Jindal | Assosiate
9 | Anjali | Assosiate
10 | Durgam | Assosiate
11 | Pravalika | Assosiate
12 | Nandini | SE
13 | Sai | SE
14 | Chirag | SE
Java Backend Expert
UI Expert